## Estimate
Project Name: |  | LEARNING ENGLISH TOGETHER
Module Name: |  | Sprint 3
Development Team: |  | C2SE.12
Start Date: |  | 2021-11-05
End Date: |  | 2021-01-06
On Time
No. | Member Name |  | Estimate |  |  |  | Lately
1 | Ha | Lê Thanh Hà | 56 |  |  |  | Early
2 | Hieu | Lê Xuân Hiếu | 56 |  |  |  | Unfinished
3 | My | Ngô Ngọc Mỹ | 53
4 | Thong | Đoàn Trung Thông | 59
Total |  |  | 224
SPRINT 3 REPORT | Conponent | Task Name | Resposible Member | Estimate | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | 2021-06-01
| Sprint Plan Meeting |  | All member | 6 | 0
| Create Sprint Backlog for Sprint 3 |  | Ha | 6 | 0
| Create Test Plan document for Sprint 3 |  | Ha | 8 | 8 | 6 | 0
Design UI
| UI Dashboard |  | Hieu | 8 | 8 | 6 | 4 | 0
| UI Manager account |  | My | 8 | 8 | 6 | 4 | 0
| UI Admin |  | Thong | 8 | 8 | 5 | 3 | 0
| UI Event |  | Hieu | 10 | 10 | 10 | 10 | 10 | 8 | 5 | 2
| UI test case Dashboard |  | Hieu | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0
| UI test case Manager account |  | My | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0
| UI test case Admin |  | My | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 0
| UI test case Event |  | Ha | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0
Database
| Design database |  | Thong | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 0
Coding
| (Front-end) Dashboard |  | Ha | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
| (Front-end) Manager account |  | Hieu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0
| (Front-end) Admin |  | Ha | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 3 | 0
| (Front-end) Event |  | My | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 2 | 0
| (Back-end) Dashboard |  | My | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
| (Back-end) Manager account |  | Thong | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 4 | 0
| (Back-end) Admin |  | Thong | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 2 | 0
| (Back-end) Event |  | Thong | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 4 | 0
Testing and fix bug
| Design Test Case for (Front-end) Dashboard |  | My | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 1 | 0
| Design Test Case for (Front-end) Manager account |  | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 1 | 0
| Design Test Case for (Front-end) Admin |  | Hieu | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design Test Case for (Front-end) Event |  | My | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
| Design Test Case for (Back-end) Dashboard |  | Hieu | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
| Design Test Case for (Back-end) Manager account |  | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0
| Design Test Case for (Back-end) Admin |  | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
| Design Test Case for (Back-end) Event |  | Hieu | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
Fix Bug & Release Sprint 3
| Implement test case |  | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0
| Fix bugs and report |  | All member | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 16 | 12 | 8 | 6 | 4 | 0
| Retest |  | All member | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 0
| Closing |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | TOTAL | 224 | 212 | 203 | 191 | 180 | 172 | 162 | 151 | 143 | 137 | 131 | 121 | 111 | 98 | 86 | 78 | 68 | 56 | 46 | 33 | 20 | 6 | 0

## Actual
Project Name: |  | LEARNING ENGLISH TOGETHER
Module Name: |  | Sprint 3
Development Team: |  | C2SE.12
Start Date: |  | 2021-11-05
End Date: |  | 2021-01-06
On Time
No. | Member Name |  | Estimate | Actual |  |  | Lately
1 | Ha | Lê Thanh Hà | 40 | 60 |  |  | Early
2 | Hieu | Lê Xuân Hiếu | 42 | 60 |  |  | Unfinished
3 | My | Ngô Ngọc Mỹ | 41 | 63
4 | Thong | Đoàn Trung Thông | 44 | 67
Total |  |  | 167 | 250
SPRINT 1 REPORT | Conponent | Task Name | Resposible Member | Actual | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | 2021-05-29 | 2021-05-30 | 2021-05-31 | 2021-06-01
| Sprint Plan Meeting |  | All member | 6 | 0
| Create Sprint Backlog for Sprint 1 |  | Ha | 6 | 0
| Create Test Plan document for Sprint 1 |  | Ha | 8 | 8 | 2 | 0
Design UI
| UI Dashboard |  | Hieu | 8 | 8 | 6 | 4 | 3 | 0
| UI Manager account |  | My | 8 | 8 | 6 | 4 | 0
| UI Admin |  | Thong | 8 | 8 | 5 | 3 | 0
| UI Event |  | Hieu | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 0
| UI test case Dashboard |  | Hieu | 6 | 6 | 6 | 6 | 6 | 4 | 3 | 0
| UI test case Manager account |  | My | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0
| UI test case Admin |  | My | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 0
| UI test case Event |  | Ha | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0
Database
| Design database |  | Thong | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 0
Coding
| (Front-end) Dashboard |  | Ha | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
| (Front-end) Manager account |  | Hieu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0
| (Front-end) Admin |  | Ha | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 4 | 0
| (Front-end) Event |  | My | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 3 | 0
| (Back-end) Dashboard |  | My | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
| (Back-end) Manager account |  | Thong | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 4 | 2 | 0
| (Back-end) Admin |  | Thong | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 4 | 0
| (Back-end) Event |  | Thong | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 4 | 0
Testing and fix bug
| Design Test Case for (Front-end) Dashboard |  | My | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 1 | 0
| Design Test Case for (Front-end) Manager account |  | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 1 | 0
| Design Test Case for (Front-end) Admin |  | Hieu | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design Test Case for (Front-end) Event |  | My | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 0
| Design Test Case for (Back-end) Dashboard |  | Hieu | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 0
| Design Test Case for (Back-end) Manager account |  | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0
| Design Test Case for (Back-end) Admin |  | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
| Design Test Case for (Back-end) Event |  | Hieu | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
Fix Bug & Release Sprint 1
| Implement test case |  | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0
| Fix bugs and report |  | All member | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 16 | 12 | 8 | 6 | 4 | 0
| Retest |  | All member | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 0
| Closing |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | TOTAL | 224 | 212 | 199 | 191 | 183 | 174 | 166 | 155 | 147 | 137 | 131 | 125 | 115 | 102 | 88 | 80 | 68 | 56 | 46 | 33 | 26 | 6 | 0

## Chart
Burn down chart Sprint 3
Estimate | Actual | Date
212 | 212 | 2021-05-11
203 | 199 | 2021-05-12
191 | 191 | 2021-05-13
180 | 183 | 2021-05-14
172 | 174 | 2021-05-15
162 | 166 | 2021-05-16
151 | 155 | 2021-05-17
143 | 147 | 2021-05-18
137 | 137 | 2021-05-19
131 | 131 | 2021-05-20
121 | 125 | 2021-05-21
111 | 115 | 2021-05-22
98 | 102 | 2021-05-23
86 | 88 | 2021-05-24
78 | 80 | 2021-05-25
68 | 68 | 2021-05-26
56 | 56 | 2021-05-27
46 | 46 | 2021-05-28
33 | 33 | 2021-05-29
20 | 26 | 2021-05-30
6 | 6 | 2021-05-31
0 | 0 | 2021-06-01