## Estimate
Project Name: |  | LEARNING ENGLISH TOGETHER
Module Name: |  | Sprint 2
Development Team: |  | C2SE.12
Start Date: |  | 13/4/2021
End Date: |  | 2021-10-05
On Time
No. | Member Name |  | Estimate |  |  |  | Lately
1 | Ha | Lê Thanh Hà | 61 |  |  |  | Early
2 | Hieu | Lê Xuân Hiếu | 67 |  |  |  | Unfinished
3 | My | Ngô Ngọc Mỹ | 65
4 | Thong | Đoàn Trung Thông | 66
Total |  |  | 259
SPRINT 2 REPORT | Conponent | Task Name | Resposible Member | Estimate | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10
| Sprint Plan Meeting |  | All member | 6 | 0
| Create Sprint Backlog for Sprint 2 |  | Ha | 6 | 0
| Create Test Plan document for Sprint 2 |  | Ha | 8 | 8 | 6 | 0
Design UI
| UI Find a helper |  | Hieu | 8 | 8 | 6 | 4 | 0
| UI Support for user |  | My | 8 | 8 | 6 | 4 | 0
| UI Search user |  | Thong | 8 | 8 | 5 | 3 | 0
| UI Learn Vocabulary |  | Hieu | 10 | 10 | 10 | 10 | 10 | 8 | 5 | 2
| UI Quiz |  | Hieu | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0
| UI test case Find a helper |  | My | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0
| UI test case Support for user |  | My | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 0
| UI test case Search user |  | Thong | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0
| UI test case Learn Vocabulary |  | Hieu | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
| UI test case Quiz |  | Ha | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
Database
| Design database |  | Thong | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 0
Coding
| (Front-end) Find a helper |  | Hieu, Ha | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 0
| (Front-end) Support for user |  | My | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
| (Front-end) Search user |  | Ha | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
| (Front-end) Learn Vocabulary |  | Ha | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 2 | 0
| (Front-end) Quiz |  | Hieu | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 2 | 0
| (Back-end) Find a helper |  | My | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0
| (Back-end) Support for user |  | My | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 0
| (Back-end) Search user |  | Thong | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0
| (Back-end) Learn Vocabulary |  | Thong | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 2 | 0
| (Back-end) Quiz |  | Thong | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 4 | 0
Testing and fix bug
| Design Test Case for (Front-end) Find a helper |  | My | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 1 | 0
| Design Test Case for (Front-end) Support for user |  | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 1 | 0
| Design Test Case for (Front-end) Search user |  | Hieu | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design Test Case for (Front-end) Learn Vocabulary |  | My | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0
| Design Test Case for (Front-end) Quiz |  | Hieu | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0
| Design Test Case for (Back-end) Find a helper |  | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design Test Case for (Back-end) Support for user |  | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design Test Case for (Back-end) Search user |  | Hieu | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design Test Case for (Back-end) Learn Vocabulary |  | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design Test Case for (Back-end) Quiz |  | Hieu | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
Fix Bug & Release Sprint 2
| Implement test case |  | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 4
| Fix bugs and report |  | All member | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 11 | 7 | 5 | 3 | 2 | 0
| Retest |  | All member | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 7 | 5 | 3 | 2 | 0
| Closing |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | TOTAL | 259 | 247 | 238 | 226 | 215 | 207 | 197 | 186 | 174 | 160 | 152 | 142 | 132 | 121 | 107 | 97 | 89 | 79 | 71 | 61 | 53 | 45 | 27 | 22 | 16 | 12 | 8 | 6 | 0

## Actual
Project Name: |  | LEARNING ENGLISH TOGETHER
Module Name: |  | Sprint 2
Development Team: |  | C2SE.12
Start Date: |  | 13/4/2021
End Date: |  | 2021-10-05
On Time
No. | Member Name |  | Estimate | Actual |  |  | Lately
1 | Ha | Lê Thanh Hà | 61 | 65 |  |  | Early
2 | Hieu | Lê Xuân Hiếu | 67 | 70 |  |  | Unfinished
3 | My | Ngô Ngọc Mỹ | 65 | 69
4 | Thong | Đoàn Trung Thông | 66 | 73
Total |  |  | 259 | 277
SPRINT 2 REPORT | Conponent | Task Name | Resposible Member | Actual | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11
| Sprint Plan Meeting |  | All member | 6 | 0
| Create Sprint Backlog for Sprint 2 |  | Ha | 6 | 4
| Create Test Plan document for Sprint 2 |  | Ha | 8 | 8 | 6 | 0
Design UI
| UI Find a helper |  | Hieu | 8 | 8 | 6 | 3 | 0
| UI Support for user |  | My | 8 | 8 | 6 | 4 | 2 | 0
| UI Search user |  | Thong | 8 | 8 | 5 | 3 | 0
| UI Learn Vocabulary |  | Hieu | 10 | 10 | 10 | 10 | 10 | 8 | 4 | 0
| UI Quiz |  | Hieu | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0
| UI test case Find a helper |  | My | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0
| UI test case Support for user |  | My | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 0
| UI test case Search user |  | Thong | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0
| UI test case Learn Vocabulary |  | Hieu | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0
| UI test case Quiz |  | Ha | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
Database
| Design database |  | Thong | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 0
Coding
| (Front-end) Find a helper |  | Hieu, Ha | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 0
| (Front-end) Support for user |  | My | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
| (Front-end) Search user |  | Ha | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
| (Front-end) Learn Vocabulary |  | Ha | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 3 | 0
| (Front-end) Quiz |  | Hieu | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 4 | 2 | 0
| (Back-end) Find a helper |  | My | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0
| (Back-end) Support for user |  | My | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0
| (Back-end) Search user |  | Thong | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0
| (Back-end) Learn Vocabulary |  | Thong | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 2 | 0
| (Back-end) Quiz |  | Thong | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 0
Testing and fix bug
| Design Test Case for (Front-end) Find a helper |  | My | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design Test Case for (Front-end) Support for user |  | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 1 | 0
| Design Test Case for (Front-end) Search user |  | Hieu | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design Test Case for (Front-end) Learn Vocabulary |  | My | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0
| Design Test Case for (Front-end) Quiz |  | Hieu | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0
| Design Test Case for (Back-end) Find a helper |  | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design Test Case for (Back-end) Support for user |  | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design Test Case for (Back-end) Search user |  | Hieu | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design Test Case for (Back-end) Learn Vocabulary |  | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
| Design Test Case for (Back-end) Quiz |  | Hieu | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
Fix Bug & Release Sprint 2
| Implement test case |  | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 4
| Fix bugs and report |  | All member | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 11 | 7 | 5 | 3 | 2 | 2 | 0
| Retest |  | All member | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 7 | 5 | 3 | 2 | 1 | 0
| Closing |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | TOTAL | 259 | 251 | 238 | 225 | 217 | 207 | 196 | 184 | 174 | 162 | 150 | 138 | 132 | 123 | 110 | 99 | 89 | 80 | 71 | 61 | 53 | 45 | 27 | 22 | 16 | 12 | 8 | 6 | 5 | 0

## Chart
Burn down chart Sprint 2
Estimate | Actual | Date
247 | 253 | 2021-04-13
238 | 240 | 2021-04-14
226 | 228 | 2021-04-15
215 | 217 | 2021-04-16
207 | 209 | 2021-04-17
197 | 199 | 2021-04-18
186 | 188 | 2021-04-19
174 | 183 | 2021-04-20
160 | 162 | 2021-04-21
152 | 154 | 2021-04-22
142 | 144 | 2021-04-23
132 | 134 | 2021-04-24
121 | 123 | 2021-04-25
107 | 111 | 2021-04-26
97 | 105 | 2021-04-27
89 | 91 | 2021-04-28
79 | 81 | 2021-04-29
71 | 73 | 2021-04-30
61 | 63 | 2021-05-01
53 | 55 | 2021-05-02
45 | 47 | 2021-05-03
27 | 29 | 2021-05-04
22 | 24 | 2021-05-05
16 | 18 | 2021-05-06
12 | 14 | 2021-05-07
8 | 10 | 2021-05-08
6 | 8 | 2021-05-09
0 | 2 | 2021-05-10
| 0 | 2021-05-11